Black Forest Excavation LLC

678 Dent rd, Prattsville NY, 12468

518-925-9468

Blackforestexcavation@gmail.com

Proposal

Windham Pines

618 and 628 Mitchell Hollow rd

Windham NY

12496

Scope of work:

- Clearing of trees and brush, Removal of all trees, stumps and brush from site. Forestry mulching and bush hogging as necessary to achieve 50’ ROW by 2,100’ with  turnaround, 5 days total - $21,600.00

- 50’ Construction entrance installed - $2,300.00

- Removal of sod and topsoil to be stockpiled and road subgrade to be cut in with ditching and proof rolled prior to placement of underlayment fabric, 5 days total - $21,600.00

- Road fabric installed - $5,650.00

- Estimated 2,940 tons of 6” minus road base delivered - $52,920.00

- Grading of road base 3 days - $10,800.00

- Estimated 840 tons of Item 4 delivered - $14,700.00

- Grading of Item 4 2 days - $7,200.00

- Installation of 1,100 feet of silt fencing - $4,160.00

- 327 tons of fill material for approach and departure of bridge - $$6,376.00

Total Estimated Price - $147,306.00