NOVA-FIELD

Means & Methods Knowledge Base

NOVATerra Intelligence Layer  |  Version 1.0

"The drawings show WHAT. This document teaches the AI HOW."

| AUTHOR | ROLE | EXPERTISE |
| --- | --- | --- |
| Mike DeLuca | Field Reality | Crew compositions, production rates, equipment, profitable sequencing |
| Paul Franklin | 4D Sequencing | Construction as a time-based process — what gates what and why |
| Sarah Chen | AI Structure | Production rates in units, dependency logic, computation rules |

SECTION 1: CONSTRUCTION SEQUENCING

1.1  Standard Commercial Building Sequence

Master Dependency Chain:

SITE WORK  →  FOUNDATIONS  →  STRUCTURE  →  ENVELOPE  →  ROUGH-INS  →  FINISHES  →  COMMISSIONING  →  PUNCH LIST

AI RULE: Each phase gates the next. No phase can fully complete until its predecessor is ≥80% complete. Partial overlaps are permitted under specific conditions defined below.

PHASE 1: SITE WORK

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | None — begins at permit issuance |
| Duration Driver | Earthwork volume (CY), dewatering, utility conflicts |
| Weather Sensitivity | Halts below 20°F or heavy rain if soil moisture exceeds compaction spec |

PHASE 2: FOUNDATIONS

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | Site work ≥80% in foundation zone |
| Duration Driver | Soil bearing confirmation, waterproofing cure times, backfill sequencing |
| Weather Sensitivity | Concrete pours: 40°F minimum |

PHASE 3: STRUCTURE

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | Foundations at design strength (28 days concrete) |
| Duration Driver | Steel lead time, crane availability, form cycle, weather |
| Weather Sensitivity | Concrete: 40°F min. Steel erection: halt winds >25 mph |

PHASE 4: ENVELOPE

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | Structure complete per zone (can begin lower floors while upper framing) |
| Duration Driver | Curtain wall / storefront lead times, envelope type |
| Weather Sensitivity | Masonry: 40°F. Membranes: 40°F. All: no rain |

PHASE 5: MEP ROUGH-INS

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | Floor dried in + rough structure complete + coordination drawings approved |
| Duration Driver | BIM clash detection, structural penetrations, coordination sequence |
| Weather Sensitivity | Interior — weather-protected. Penetrations: no freeze |

PHASE 6: FINISHES

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | Rough-ins inspected, building dried in, HVAC operational or temp heat active |
| Duration Driver | Sequence discipline, floor protection, inspection timing |
| Weather Sensitivity | HVAC must maintain 50–90°F, 20–65% RH for finishes |

PHASE 7: COMMISSIONING

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | All systems installed and operational |
| Duration Driver | AHJ scheduling, Cx agent availability, TAB coordination |
| Weather Sensitivity | Interior — N/A |

PHASE 8: PUNCH LIST

| ATTRIBUTE | DETAIL |
| --- | --- |
| Predecessor | Certificate of Occupancy or TCO issued |
| Duration Driver | QC program quality during construction |
| Weather Sensitivity | Interior — N/A |

Phase 2: Foundation Activity Sequence

| ACTIVITY | DEPENDENCY | OVERLAPPABLE? |
| --- | --- | --- |
| Soil bearing test/observation | Excavation complete | NO — observation required |
| Form footings | Bearing confirmed | Yes — by grid |
| Pour footings | Formwork + rebar inspection | NO — inspection required |
| Cure time (footings) | Pour complete | NO — min 7 days for stripping |
| Foundation walls (CMU or CIP) | Footings at design strength | Yes — by bay |
| Waterproofing | Foundation walls complete | NO — substrate dry/cured |
| Backfill | Waterproofing + drainage board + structure anchors walls | NO |
| Underslab utilities | After backfill | Yes — by area |
| Slab-on-grade | Underslab complete + compaction tested | By pour section |

AI FLAG: Backfill against foundation walls before structure is erected creates lateral load risk — flag this sequencing in any estimate.

Phase 5: MEP Coordination Sequence

Strict sequencing within MEP rough-in phase:

AI RULE: In ceiling cavities less than 18" clear, coordination drawings are not optional. Flag every project with less than 24" ceiling cavity as a coordination risk.

1.2  Sequencing by Structure Type

| VARIABLE | STEEL FRAME | CIP CONCRETE | WOOD FRAME | CMU LOAD-BEARING |
| --- | --- | --- | --- | --- |
| Primary schedule driver | Steel lead time (16–24 wk) | Concrete cure cycle | Framing speed | Masonry production |
| Weather sensitivity | High (erection) | Very high (pour/cure) | High (drying) | High (mortar) |
| Typical floor cycle | 1–2 weeks/floor | 5–10 days/floor (flying form) | 3–5 days/floor | 7–14 days/floor |
| Crane dependency | Always | Usually | Rarely | Rarely |
| Typical height range | Unlimited | Unlimited | ≤6 stories | ≤6 stories |
| MEP coordination complexity | High (open web joists) | High (slab penetrations) | Moderate | Moderate |

1.3  Long-Lead Items: Critical Order Windows

AI RULE: Failure to order long-lead items on time is the #1 avoidable schedule delay cause. Flag any item on this list.

| ITEM | LEAD TIME | ORDER MILESTONE |
| --- | --- | --- |
| Structural steel (fabricated) | 16–24 weeks | At schematic design completion |
| Elevators | 26–52 weeks | At DD completion / permit submission |
| Curtain wall system | 20–32 weeks | At CD 50% |
| Main electrical switchgear (>400A) | 20–52 weeks | At DD completion |
| Generator (>150 kW) | 20–40 weeks | At DD completion |
| Cooling tower | 16–24 weeks | At CD 50% |
| Custom precast panels | 20–28 weeks | At CD 50% |
| Medium voltage transformers | 40–65 weeks (current) | AT SCHEMATIC DESIGN — CRITICAL |
| Fire pump assembly | 16–24 weeks | At CD 90% |
| Custom storefront | 10–14 weeks | At permit |
| Stair pans (custom) | 12–16 weeks | At CD 90% |

1.4  Overlap Matrix: What Can Run Concurrently

| PHASE A | PHASE B | OVERLAP? | CONDITION |
| --- | --- | --- | --- |
| Site work (upper site) | Foundations (lower site) | ✓ YES | Separate zones |
| Steel erection (upper floors) | MEP rough-in (lower floors) | ✓ YES | 2-floor buffer minimum |
| Envelope (lower floors) | Rough-in (same floors) | ✓ YES | Floor dried in |
| Drywall hang | Tape/finish (different floors) | ✓ YES | 1 floor offset |
| Rough-in | Framing | ✗ NO | Framing must be inspected first |
| Painting | Flooring installation | ✗ NO | Paint must be complete |
| Commissioning | Punch list | ✓ YES | Zone-by-zone |

1.5  Weather-Dependent Activities

| ACTIVITY | TEMP LIMIT | PRECIP LIMIT | NOTES |
| --- | --- | --- | --- |
| Concrete pour | 40°F rising (35°F w/protection) | No active rain | Cold weather plan required <40°F |
| Masonry | 40°F rising (35°F w/enclosure) | No rain | Mortar freezes; joints fail |
| Roofing (membrane) | 40°F min for adhesives | No moisture | TPO/EPDM won't cure |
| Painting (exterior) | 50°F; surface 5°F above dew point | No rain / <85% RH |  |
| Steel erection | No temp limit | Wind >25 mph = stop | OSHA 1926.1416 |
| Earthwork/compaction | 28°F | Saturated soil = stop | Proctor test governs |
| Paving (asphalt) | 50°F air and rising | No rain | Asphalt cools below 275°F = reject |
| Waterproofing (liquid) | 40°F min | No moisture | Surface prep critical |
| Spray fireproofing | 40°F min | No moisture | Humidity <90% |

SECTION 2: CREW COMPOSITIONS & PRODUCTION RATES

NOTE: All rates are expressed as [Unit/Crew-Day] based on 8-hour shift. Apply: 10-hr = 1.15×; 12-hr = 1.25×. Region factors: NYC Metro = 0.70×; Northeast = 0.85×; Midwest = 1.00× (base); Southeast = 1.05×.

2.1  Concrete

Footing / Foundation Wall Crew

| ELEMENT | DETAIL |
| --- | --- |
| Crew composition | 1 Foreman + 3 Carpenters (forms) + 2 Rod Busters + 4 Laborers |
| Form erection | 200–350 SF contact area/crew/day (complex geometry = 150 SF) |
| Rebar placement | 1,500–2,500 LB/rod buster/day |
| Pour rate (pump) | 60–100 CY/hour |
| Pour rate (crane + bucket) | 20–35 CY/hour |
| Pour crew | 1 Foreman + 1 CY operator + 2 Vibrators + 2 Laborers (screed) + 1 Pump operator |

Slab on Grade Crew

| CONDITION | PRODUCTION |
| --- | --- |
| Standard flatwork (no special finish) | 2,000–4,000 SF/day |
| Fine finish (power trowel) | 1,500–2,500 SF/day |
| Polished concrete | 500–1,000 SF/day per polishing crew |
| Crew composition | 1 Foreman + 2 Finishers + 4 Laborers |

Concrete Cost Flags

2.2  Structural Steel Erection

Crew Composition

Core crew: 1 Foreman + 4 Connectors + 2 Bolters + 1 Crane Operator + 1 Oiler + 1 Rigger + 1 Surveyor (shared)

Production Rates by Building Type

| PROJECT TYPE | TONS/DAY | NOTES |
| --- | --- | --- |
| Simple industrial (warehouse, box) | 8–15 tons/day | Repetitive, large members |
| Mid-rise office/commercial | 4–8 tons/day | Mixed members, more connections |
| High-rise (above 20 floors) | 2–4 tons/day | Wind, logistics, pick complexity |
| Structural mezzanine | 3–6 tons/day | Tight access, complex detailing |

| ACTIVITY | RATE |
| --- | --- |
| Simple picks (columns, beams) | 12–20 picks/hour |
| Complex picks (trusses, long-span) | 4–8 picks/hour |
| Standard bolt pattern | 200–400 bolts/crew/day |
| High-strength tension-control bolts | 150–300/crew/day |

AI FLAG: Erection drawings and anchor bolt plans must be approved before mobilization. Each RFI during erection costs approximately 1–3 days of schedule.

2.3  Masonry

Standard crew: 1 Mason Foreman + 4 Journeymen Masons + 4 Tenders (2 tenders per mason)

| UNIT TYPE | UNITS/MASON/DAY | SF/MASON/DAY | NOTES |
| --- | --- | --- | --- |
| 8" CMU (standard) | 125–175 | 110–155 | Normal running bond |
| 12" CMU | 90–130 | 90–130 | Heavier — fatigue factor |
| 4" brick (running bond) | 350–500 | 100–145 | Experienced mason |
| 4" brick (complex pattern) | 200–300 | 58–87 | Soldier course, herringbone |
| Stone veneer (cut) | — | 30–60 | Complex — high skill required |
| Grout (CMU fill) | 1,500–2,500 LF cells/day | — | Low-lift grouting |

2.4  Metal Stud Framing

Typical crew: 1 Foreman + 3 Carpenters + 1 Laborer

| WORK TYPE | LF OR SF PER CARPENTER/DAY |
| --- | --- |
| Exterior wall track/stud layout | 150–250 LF/day |
| Interior partition layout + framing | 200–350 LF/day |
| Interior non-structural partition (fully framed) | 300–500 SF wall/day |
| Exterior load-bearing stud wall (complex) | 150–250 SF wall/day |
| Ceiling framing (soffits, clouds) | 200–350 SF/day |
| Framing around openings (doors, windows) | 4–8 openings/carpenter/day |

AI FLAG: High door density projects (hospitals, schools) have 20–30% lower linear footage productivity vs. open office floor plates.

2.5  Drywall: Hanging & Finishing

Hanging

Crew: 1 Foreman + 4 Hangers + 2 Laborers

| CONDITION | SF/HANGER/DAY |
| --- | --- |
| Open flat walls, 9' ceiling, standard | 1,200–1,800 SF |
| Corridors + many rooms | 800–1,200 SF |
| High walls (12'–16') | 800–1,200 SF |
| Ceilings (flat) | 600–1,000 SF |
| Complex ceilings (soffits, curves) | 300–600 SF |

Taping & Finishing

Crew: 1 Foreman + 3 Finishers + 1 Helper

| OPERATION | SF/FINISHER/DAY |
| --- | --- |
| Tape (coat 1) | 1,500–2,500 SF |
| Second coat | 2,000–3,000 SF |
| Third coat / skim | 1,500–2,000 SF |
| Sanding | 1,000–1,500 SF |

Finish Level Reference

| LEVEL | DESCRIPTION | TYPICAL USE |
| --- | --- | --- |
| L1 | Tape embedded only | Fire-rated assemblies hidden above tile |
| L2 | Tape + one coat | Water-resistant board in wet areas |
| L3 | Two coats | Texture or heavy wall covering |
| L4 (standard) | Three coats | Flat/eggshell paint |
| L5 (premium) | Skim coat over L4 | High-gloss paint, critical lighting |

2.6  Painting

Crew: 1 Foreman + 3–4 Painters + 1 Helper

| SYSTEM | SF/PAINTER/DAY | NOTES |
| --- | --- | --- |
| Prime coat (roller, flat walls) | 2,500–4,000 SF | Open floor plates |
| Finish coat (roller) | 2,000–3,500 SF | Open floor plates |
| Corridors + doors (cut-in heavy) | 1,000–1,800 SF | High linear trim |
| Ceiling (roller) | 2,000–3,500 SF | No obstructions |
| Ceiling (spray, commercial) | 5,000–8,000 SF | Masking time not included |
| Epoxy (2-part, roller) | 800–1,500 SF | Prep time significant |
| Staining (millwork) | 200–400 LF/day | Wipe + seal system |

AI RULE: Every additional coat = 70–80% of the base coat production rate. Never assume 100% re-coat rate.

2.7  Flooring

| TYPE | SF/INSTALLER/DAY | CREW | NOTES |
| --- | --- | --- | --- |
| VCT (vinyl composition tile) | 500–800 SF | 2–3 | Adhesive, seaming, rolling |
| LVT/LVP (luxury vinyl plank) | 600–1,000 SF | 2 | Floating faster; glue-down slower |
| Carpet tile (2×2) | 800–1,200 SF | 2 |  |
| Broadloom carpet | 600–1,000 SF | 2–3 | Seaming reduces rate |
| Porcelain tile (12×12 grid) | 150–250 SF | 2 | Thin-set, layout lines |
| Large format tile (24×24+) | 80–150 SF | 2–3 | Back-butter, leveling clips |
| Epoxy terrazzo (poured) | 50–100 SF | 3–4 | High skill, long cure |
| Hardwood (strip, nailed) | 300–500 SF | 2 |  |
| Polished concrete (grind + seal) | 400–800 SF | 2 | Separate from pour phase |

AI RULE: Flooring is the 'no-go-back' trade. Once down, heavy deliveries require floor protection. Budget $0.35–$0.75/SF floor protection cost on all finish-phase projects.

2.8  Ceiling Grid (Suspended ACT)

| CONDITION | SF/INSTALLER/DAY |
| --- | --- |
| Open, standard 2×4 grid | 600–900 SF |
| Open, 2×2 grid | 500–800 SF |
| Heavy obstructions (lots of MEP) | 350–550 SF |
| Custom/specialty grid (tegular, reveals) | 300–500 SF |
| Grid in corridors | 200–400 LF |

AI FLAG: ACT grid is the finish-phase coordinator. All above-ceiling MEP must be complete, tested, and accessible-panel locations confirmed before grid installation begins.

2.9  MEP Rough-In Production Rates

Plumbing

| ACTIVITY | RATE | UNIT |
| --- | --- | --- |
| Waste + vent rough-in (standard) | 4–8 | Fixtures/plumber/day |
| Supply rough-in (copper) | 80–120 | LF/plumber/day |
| Cast iron stack | 20–40 | LF/plumber/day |
| PVC DWV | 80–150 | LF/plumber/day |
| Trim-out (fixture set) | 6–10 | Fixtures/plumber/day |
| Underground sanitary (2-man crew) | 60–100 | LF/crew/day |

Electrical

| ACTIVITY | RATE | UNIT |
| --- | --- | --- |
| EMT conduit run (straight) | 150–250 | LF/electrician/day |
| Conduit in tight ceiling cavity | 60–100 | LF/electrician/day |
| Wire pull (parallel circuits) | 400–800 | LF/electrician/day |
| Device rough (receptacles, switches) | 15–25 | Devices/electrician/day |
| Device trim (devices + plates) | 25–50 | Devices/electrician/day |
| Panel wiring | 1 | Panel/electrician/day |
| Light fixture rough | 20–35 | Fixtures/electrician/day |
| Light fixture trim | 15–25 | Fixtures/electrician/day |

HVAC / Mechanical

| ACTIVITY | RATE | UNIT |
| --- | --- | --- |
| Rectangular duct (main trunk) | 150–300 | LB sheet metal/crew/day |
| Rectangular duct (branch distribution) | 80–150 | LB/crew/day |
| Flex duct connections | 15–30 | Connections/mechanic/day |
| VAV box set | 4–8 | Units/mechanic/day |
| Fan coil unit set | 3–6 | Units/crew/day |
| Pipe insulation | 100–200 | LF/insulator/day |

SECTION 3: EQUIPMENT & LOGISTICS

3.1  Crane Decision Matrix

| FACTOR | SUGGESTS MOBILE CRANE | SUGGESTS TOWER CRANE |
| --- | --- | --- |
| Building height | ≤6 stories | ≥7 stories |
| Pick duration | Short (<4 weeks) | Extended (≥6 weeks) |
| Site access | Open, mobile access possible | Tight urban site |
| Steel tonnage | <200 tons total | >200 tons total |
| Picks per day | <30 picks/day | >50 picks/day |
| Material hoisting ongoing | Not needed after structure | Needed throughout project |

Tower Crane Cost Factors

| COST ITEM | RANGE |
| --- | --- |
| Mobilization / demobilization | $35,000–$120,000 |
| Monthly rental | $18,000–$45,000/month |
| Operator (union NYC) | $95–$125/hour including benefits |
| Foundation anchor (tied to structure) | $25,000–$80,000 |
| Climbing (per climb) | $15,000–$40,000 |

3.2  Concrete Pump vs. Crane-and-Bucket

| FACTOR | USE PUMP | USE CRANE + BUCKET |
| --- | --- | --- |
| Pour volume | >50 CY | Any volume |
| Pour rate required | High (>40 CY/hr) | Lower acceptable |
| Crane availability | Not available / crane busy | Crane available |
| Cost | Pump: $800–$2,500/day + line | Crane time only |

NOTE: On urban sites, a concrete pump with boom can place concrete without occupying the tower crane — which is often more valuable doing steel or other picks simultaneously. Always evaluate crane productivity vs. pump cost.

3.3  Scaffold vs. Aerial Lift

| FACTOR | SCAFFOLDING | SCISSORS / BOOM LIFT |
| --- | --- | --- |
| Best for | Sustained access >2 weeks same zone | Short, moving access |
| Load capacity | Heavy materials (masonry) | Personnel + light tools |
| Height | Unlimited (frame scaffold) | Scissors to 50', boom to 150' |
| Setup cost | $4–10/SF/month | $800–$2,500/day rental |
| Best use cases | Masonry, exterior envelope | Interior drywall, MEP, finishes |

3.4  Temporary Facilities

| ITEM | WHEN NEEDED | TYPICAL COST |
| --- | --- | --- |
| Construction trailer (GC) | Mobilization through CO | $800–$2,500/month |
| Temporary power (service entrance) | Before underground complete | $5,000–$25,000 install + $800–$2,000/month |
| Temporary water | Immediately | $500–$2,000 tap + meter |
| Dumpsters (30 CY) | Throughout | $500–$900/pull |
| Portable toilets | Throughout (1 per 10 workers) | $150–$300/month each |
| Construction fencing (chain link) | Mobilization | $3–8/LF installed |
| Temp lighting (interior) | Before permanent energized | $0.15–$0.35/SF installed |
| Street closure permits (NYC) | Per work zone | $500–$5,000 + NYPD coordination |

SECTION 4: GENERAL CONDITIONS COST DRIVERS

4.1  Project Duration Impact on General Conditions

AI RULE: General conditions cost is ~70% time-based, ~30% fixed. Every month of schedule extension = 4.3 × weekly GC burn rate in added cost.

GC % by Project Size

| PROJECT SIZE | GC % RANGE | WEEKLY GC BURN RATE |
| --- | --- | --- |
| < $1M | 18–25% | $3,000–$5,000/week |
| $1M–$5M | 14–20% | $8,000–$14,000/week |
| $5M–$25M | 10–16% | $20,000–$35,000/week |
| $25M–$100M | 8–12% | $60,000–$100,000/week |
| > $100M | 6–10% | $100,000+/week |

4.2  Field Staff by Project Size

| PROJECT SIZE | SUPER | PM | FIELD ENGINEER | PROJECT EXECUTIVE |
| --- | --- | --- | --- | --- |
| < $500K | 1 (shared) | 1 (dual role) | 0 | 0.1 (oversight) |
| $500K–$2M | 1 | 1 (may share) | 0 | 0.25 |
| $2M–$10M | 1 | 1 | 1 | 0.5 |
| $10M–$50M | 1–2 | 1 | 1–2 | 0.5 |
| > $50M | 2–3 | 1–2 | 2–4 | 1 |

Burdened Labor Rates — NYC Metro (2024–2025)

| ROLE | SALARY RANGE | TOTAL BURDENED ANNUAL | WEEKLY COST |
| --- | --- | --- | --- |
| Superintendent | $130K–$185K | $176K–$250K | $3,385–$4,808 |
| Project Manager | $110K–$165K | $149K–$223K | $2,865–$4,288 |
| Field Engineer | $75K–$105K | $101K–$142K | $1,942–$2,731 |
| Project Executive | $180K–$275K | $243K–$371K | $4,673–$7,135 |

4.3  Insurance and Bonding

| COVERAGE | TYPICAL COST |
| --- | --- |
| General Liability | 0.5–1.5% of contract |
| Builder's Risk | 0.4–0.8% of project value |
| Workers' Comp (varies by trade) | 5–30% of labor cost |
| Umbrella | 0.2–0.5% of contract |
| Performance & Payment Bond | 0.5–1.5% of contract |
| TOTAL (typical range) | 3–6% of contract value |

Workers' Comp by Trade (Approximate)

| TRADE | WC RATE (% OF LABOR) |
| --- | --- |
| Ironworkers | 18–28% |
| Roofers | 20–30% |
| Concrete (structural) | 10–18% |
| Electrical | 5–10% |
| Drywall | 6–12% |

4.4  Permit and Fee Structures

NOTE: Highly jurisdiction-dependent. NYC Metro representative values shown. Always verify per project location.

| FEE TYPE | BASIS | TYPICAL RANGE |
| --- | --- | --- |
| Building permit | Per $1,000 construction value | $5–$15/$1,000 |
| Plan review | Flat or per page | $1,500–$15,000 |
| Plumbing permit | Per fixture | $25–$75/fixture |
| Electrical permit | Per circuit or value | $500–$5,000 |
| Elevator permit | Per cab | $2,000–$8,000 |
| NYC sidewalk shed | Per LF/year | $7–$15/LF/year |
| TOTAL PERMITS (rough) | % of construction cost | 1.5–4% |

4.5  Temporary Protection Costs

| ITEM | WHEN | COST ESTIMATE |
| --- | --- | --- |
| Winter enclosures (heated) | Concrete/masonry <40°F | $2–$5/SF/month enclosed |
| Heating (propane/temp) | Interior work <50°F | $800–$3,000/week per floor |
| Dust barriers (ZipWall/poly) | Occupied building work | $1–$3/LF installed |
| Floor protection (Ram Board) | Finishes in occupied/final | $0.35–$0.75/SF |
| Window protection | Masonry / spray work near glass | $0.25–$0.50/SF |

4.6  Safety Requirements (OSHA)

| THRESHOLD | REQUIREMENT |
| --- | --- |
| All projects | SDS sheets, fall protection at 6', hard hats, safety glass, hi-vis, weekly toolbox talks |
| >20 workers at peak | Dedicated site safety coordinator |
| >$10M contract (NYC) | Designated safety manager + site-specific safety plan |
| Trenching >5' deep | Competent person + shoring/sloping plan |
| Scaffold >10 feet | Competent person erection supervision |
| Any crane pick | Lift plan required; critical picks (>75% capacity) require engineer |
| Confined space work | Permit required + attendant |

AI RULE: Budget 1.0–2.5% of direct construction cost for site safety. Higher end for healthcare, occupied buildings, and complex urban sites.

4.7  Cleaning Cost Schedule

| TYPE | WHEN | COST |
| --- | --- | --- |
| Progressive cleaning | Ongoing — per phase | $0.10–$0.25/SF active work area/week |
| Post-drywall rough clean | After drywall, before flooring | $0.15–$0.30/SF |
| Pre-finish final clean | Before floor protection down | $0.20–$0.40/SF |
| Construction final clean | Post punch list | $0.30–$0.60/SF |
| Window cleaning (construction film) | At turnover | $2–$5/window |

AI RULE: Never allow cleaning to be a single line item at project end. Progressive cleaning is a direct cost of each phase. Under-budgeting progressive cleaning causes finish damage, disputes, and schedule delays.

SECTION 5: CONSTRUCTABILITY FLAGS

AI RULE: When NOVATerra detects any of the following conditions in project scope or drawings, it must raise a constructability flag with an explanation, recommended action, and estimated cost impact.

5.1  Access-Driven Difficulty

| CONDITION | FLAG CODE | SUGGESTED ACTION |
| --- | --- | --- |
| Site with <20 feet clearance on any side | TIGHT_SITE | Add premium for material staging, limited laydown, possible street permits |
| Urban infill with no street-level staging | URBAN_LOGISTICS | Add hoisting plan; just-in-time delivery premium (10–20% labor) |
| Renovation in occupied building | OCCUPIED_PHASING | Phase plan required; off-hours premium (50–100% labor uplift) |
| Water table <5 feet below slab | DEWATERING | Dewatering plan required; can add $50K–$500K to project |
| Roof work, no crane access, material >50 LB | ROOF_LOGISTICS | Crane or hoist plan required |
| Work above occupied space | OVERHEAD_PROTECTION | Debris netting or plywood deck required; phasing required |

5.2  Design-Driven Difficulty

| CONDITION | FLAG CODE | SUGGESTED ACTION |
| --- | --- | --- |
| Structural bay >40 LF no intermediate support | LONG_SPAN | Verify deflection; add camber; erection bracing cost |
| Cantilever >12 feet | CANTILEVER_RISK | Shoring until structural completion; temp support cost |
| Ceiling cavity <18" clear | TIGHT_CEILING | MEP coordination drawings required; custom products may be needed |
| Curved/non-orthogonal geometry | COMPLEX_GEOMETRY | Custom forming +25–50%; labor productivity -30–50% |
| Mixed structure types | HYBRID_STRUCTURE | Multiple trade mobilizations; interface coordination required |
| Exposed concrete/steel finish | EXPOSED_FINISH | Premium on formwork quality; grinding/blasting may be required |

5.3  Value Engineering Opportunities

NOTE: When flagged conditions are detected, NOVA should generate a VE option alongside the base estimate.

| CONDITION | VE OPPORTUNITY | TYPICAL SAVINGS |
| --- | --- | --- |
| CIP concrete structure <8 stories | Evaluate structural steel frame | Schedule savings 8–12 weeks; cost market-dependent |
| Custom curtain wall specified | Evaluate punched window + panel | 20–40% of envelope cost |
| Custom millwork specified | Evaluate semi-custom or modular casework | 25–40% of millwork cost |
| Specified stone flooring | Evaluate large-format porcelain | 30–60% of material cost |
| 2×2 ceiling tile, back-of-house | Evaluate 2×4 or eliminate grid | 15–25% of ceiling cost |
| 4-pipe fan coil system | Evaluate VRF/VRF-W | 10–20% net (case by case) |
| Plaster walls | Evaluate Level 5 drywall | 40–60% labor savings |
| Site-built millwork (reception desk) | Evaluate pre-fab modular | 20–40% savings |

5.4  MEP Coordination Challenges

AI FLAG: Any project with ceiling cavity <30", multi-tenancy MEP, or renovation of existing MEP should trigger a coordination flag.

| CHALLENGE | IMPACT | REQUIRED ACTION |
| --- | --- | --- |
| HVAC duct through structural bays | Conflicts with beams; offsets needed | BIM coordination; structural penetrations $150–$500 each |
| Plumbing stack above slab | Core drilling required | $200–$600 per core + scheduling |
| Sprinkler heads vs. ceiling grid | Head spacing must align with grid module | Coordination drawing required; relocation $50–$150/head |
| Conduit + HVAC in same joist bay | Common conflict in open web joists | Strict routing plan; first-in rules apply |
| Low-voltage through fire-rated walls | Penetration sealing required (UL) | $25–$75 per penetration (firestop + inspection) |

5.5  Phasing in Occupied Buildings

AI RULE: Any renovation in an occupied building requires a phasing plan as part of the estimate. Occupied work without a phasing plan is an incomplete scope — do not price it.

| CONDITION | LABOR PREMIUM | NOTES |
| --- | --- | --- |
| Work during business hours in occupied space | +20–35% | Noise restrictions, limited access windows |
| Work after hours (6PM–6AM) | +50–100% | Overtime + premium for all trades |
| Work with infection control (ICRA) | +30–50% | Negative pressure, barriers, protocol |
| Weekend work only | +50–75% | Limited crew availability; premium pay |
| Phased area access (one room at a time) | +40–60% | Setup/breakdown per phase; no staging |
| Dust/noise restrictions (legal, healthcare) | +25–40% | Work window limitations, slow-cut requirements |

APPENDIX: AI COMPUTATION RULES SUMMARY

NOTE: The following rules are structured for direct use in NOVATerra's estimation logic engine.

Production Rate Application Rules

| RULE | CONDITION | FACTOR / ACTION |
| --- | --- | --- |
| Market Factor | NYC Metro | 0.70× |
| Market Factor | Northeast | 0.85× |
| Market Factor | Midwest (base) | 1.00× |
| Market Factor | Southeast | 1.05× |
| Market Factor | West Coast | 0.90× |
| Shift Factor | 8-hour shift | 1.00× |
| Shift Factor | 10-hour shift | 1.15× |
| Shift Factor | 12-hour shift | 1.25× |
| Winter Factor | Nov 15–Mar 15, lat >39.5°, exposed work | 0.75–0.85× + add heating/enclosure cost |
| Long Lead Flag | Item in long-lead list, design <CDs 90% | FLAG: ORDER NOW with lead time |
| Schedule Extension | Any duration extension | Added cost = weeks × weekly GC burn rate |
| Constructability | Match against Section 5 conditions | RAISE flag with description + cost impact |

NOVA-FIELD Knowledge Base v1.0  |  NOVATerra AI Layer  |  Authors: DeLuca · Franklin · Chen  |  For internal AI consumption. All rates are representative mid-range values for estimation guidance. Final numbers require local market verification.